## Sheet1
Phase | Category | Subtasks
General MAP Configuration
1. Technical Setup: Add provision Users, Website Tracking Code, domain/subdomain mapping
[Define Roles] Marketo Users - who will need to be provisioned with what roles?
[Update Website] Add Munchkin Code to Tag Manager and add to site
2. Setup SPF/DKIM for email deliverability (IT team to update DNS settings)
[Confirm] Marketo Email domain settings work
[Set-Up] SPK/DKIM outlined in Marketo Instructions
[Set-Up] Cnames for Landing Pages to configure SSL
[Set-UP] Cname for Email "From" subdomain
[Exclude] Internal office IP addresses from Google Analytics
3. Configure Social Media accounts
4. Setup and configure third-party integrations, i.e. Zoom, Rybbon, Siftrock, Unbounce, Triblio, Typeform, etc.
5. Identify email and landing page template requirements
[Create] Wireframes - Landing Page and Email
[Review/Approve/Edit] Wireframes for LP and Email
6. Identify non-active list memberships you want to retain (if any)
7. Confirm forms to be consolidated/rebuilt
8. Design and code email and landing page templates
[Design/Deliver] initial landing page and email template design
[Review/Approve/Edit] Wireframes for LP and Email
[Code/Build] Email and Landing Page
[Implement] final email and LP templates in Marketo
[QA] final email and LP templates
9. Run tests for the Website Tracking, lead tracking and domain mapping
10. Set Up SSO Marketo - Loop in IT
[Create] admin user for IT POC
[Provide] IT with instructions
[Request] information from Marketo support for SSO configuration assistance
Salesforce Integration & Data Migration
1. [confirm & standardize] UTM fields and picklists
1. [Identify] standard and custom fields to be migrated
3. [Conduct] test integration and migration of data into a Salesforce sandbox org
4. [Resolve] any issues that arise during test migration
5. [Install] Marketo package in Salesforce
6. [Import] Leads and Contacts into MAP
7. [Setup] Marketo Sales Insight; identify pilot users to train, evaluate use cases, and build sales templates to benefit the rest of the team
8. [Create] A Sync User Profile Permissions for the new Marketo user
MAP Migration
1. Recreate forms within MAP, working closely to maintain current functionality for current Website forms
[Test] new form with new landing page functionality
2. Build landing pages
[Identify/triage] which landing pages will move over
3. Migrate key emails to Marketo
4. Import all images, PDFs, Lists, Forms, Contacts, Accounts, assets
5. Implement lead scoring model(s)
6. Implement lead lifecycle (stages, transitions, SLAs)
7. Implement lead lifecycle in Marketo Revenue Cycle Model and build any necessary automation in Marketo and/or Salesforce to handle transitions
[Set-Up] Alert in Marketo
8. Rebuild active programs in MAP and link to corresponding Salesforce campaigns
[Build] Program for Event Engagement and sync SFDC campaign
9. Create operational campaigns to optimize data hygiene in Marketo
10. Run tests on rebuilt assets, programs, and Salesforce attribution
[Resolve] any issues that arise during testing
11. IP Warming Campaign
[Determine] warming lists of highly engaged contacts
[Write] emails in Marketo
[Launch] campaign
[Schedule] meeting with Marketo Deliverability team
12. Web
[Setup/integrate] the Client site blog
[Create] redirects
[SEO] new landing pages
[Test] new form with web site page functionality
Copyright Sponge.io